## Project Planner
Sydney AirBnB Search
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1.1 Group meeting | 1 | 1 |  |  | 100%
1.2 Research for the Airbnb data | 2 | 1 |  |  | 100%
1.3 Gathering the requirements | 2 | 1 |  |  | 100%
1.4 Define tasks | 2 | 1 |  |  | 100%
1.5 Allocationg roles | 3 | 1 |  |  | 100%
1.6 Create WBS | 4 | 1 |  |  | 100%
1.7 Report back to client | 5 | 1 |  |  | 100%
2.1 Design system structure | 6 | 2 |  |  | 100%
2.2 Design UI | 7 | 2 |  |  | 100%
2.3 Create use case diagram | 6 | 1 |  |  | 100%
3.1 Code for system structure | 9 | 21 |  |  | 100%
3.2 Code for UI | 9 | 7 |  |  | 100%
4.1 Testing plan | 30 | 2 |  |  | 100%
4.2 Running Unit test | 32 | 1 |  |  | 100%
4.3 Fixing bug | 33 | 1 |  |  | 100%
4.3 Generate coverage report | 34 | 1 |  |  | 100%
4.5 Modified original code | 34 | 1 |  |  | 100%
4.6 Requirement acceptance test | 35 | 1 |  |  | 100%
5.1 Executive summary | 36 | 1 |  |  | 100%
5.2 End of project | 37 | 1 |  |  | 0%
Activity 20 |  |  |  |  | 0%
Activity 21 |  |  |  |  | 0%
Activity 22 |  |  |  |  | 0%
Activity 23 |  |  |  |  | 0%
Activity 24 |  |  |  |  | 0%
Activity 25 |  |  |  |  | 0%
Activity 26 |  |  |  |  | 0%
Activity 27 |  |  |  |  | 0%
Activity 28 |  |  |  |  | 0%
Activity 29 |  |  |  |  | 0%
Activity 30 |  |  |  |  | 0%
Activity 31 |  |  |  |  | 0%
Activity 32 |  |  |  |  | 0%
Activity 33 |  |  |  |  | 0%
Activity 34 |  |  |  |  | 0%
Activity 35 |  |  |  |  | 0%